## Sheet1
Activity ID | Activity Name | WBS Name | Plnned Strt | Planned Finish | Budgeted Total Cost
A3150 | Cabinets/Telecom Rooms | Civil works | 2023-07-18 | 2023-08-02 | 30000
A3590 | Project Start Date | Milestones | 2023-07-18 | 2023-07-19 | 0
A3610 | Prepare and Submitt Cabins Design {Schematic Design} | Submit for approval Schematic Designs | 2023-07-18 | 2023-07-25 | 3857
A3650 | Set Offices | Mobilization | 2023-07-18 | 2023-07-25 | 0
A2260 | 10 watts PA Horn Speaker Indoor type | ELV works | 2023-07-19 | 2023-08-02 | 2700
A3560 | Prepare and Submitt Master plan {Schematic Design} | Submit for approval Schematic Designs | 2023-07-19 | 2023-08-09 | 3857
A3620 | Prepare and Submitt Land scape Design {Schematic Design} | Submit for approval Schematic Designs | 2023-07-19 | 2023-07-26 | 3857
A3630 | Prepare and Submitt Departure Hall Design {Schematic Design} | Submit for approval Schematic Designs | 2023-07-19 | 2023-07-26 | 3857
A3730 | Prepare and Submitt Electerical Design {Schematic Design} | Submit for approval Schematic Designs | 2023-07-19 | 2023-07-26 | 3857
A3740 | Prepare and Submitt Mechanical design {Schematic Design} | Submit for approval Schematic Designs | 2023-07-19 | 2023-07-26 | 3857
A3750 | Prepare and Submitt Metal fence Design {Schematic Design} | Submit for approval Schematic Designs | 2023-07-19 | 2023-07-26 | 3857
A3600-20 | Schematic Design Start Date | Milestones | 2023-07-19 |  | 0
A3640 | Site Cleaning | Mobilization | 2023-07-25 | 2023-08-01 | 0
A3770 | Approved Cabins Design {Schematic Design} | Approved Schematic Designs | 2023-07-25 | 2023-08-01 | 3857
A3780 | Approved Land scape Design {Schematic Design} | Approved Schematic Designs | 2023-07-26 | 2023-08-02 | 3857
A3790 | Approved Departure Hall Design {Schematic Design} | Approved Schematic Designs | 2023-07-26 | 2023-08-02 | 3857
A3800 | Approved Electerical Design {Schematic Design} | Approved Schematic Designs | 2023-07-26 | 2023-08-02 | 3857
A3810 | Approved Mechanical design {Schematic Design} | Approved Schematic Designs | 2023-07-26 | 2023-08-02 | 3857
A3820 | Approved Metal fence Design {Schematic Design} | Approved Schematic Designs | 2023-07-26 | 2023-08-02 | 3857
A3840 | Prepare and Submitt Cabins Design {Detailed Design} | Submit for approval Detailed Design | 2023-08-01 | 2023-08-08 | 3857
A3250 | Construct Median with Interlocking Tiles | Civil works | 2023-08-02 | 2023-08-21 | 167000
A3850 | Prepare and Submitt Land scape Design {Detailed Design} | Submit for approval Detailed Design | 2023-08-02 | 2023-08-09 | 3857
A3860 | Prepare and Submitt Departure Hall Design {Detailed Design} | Submit for approval Detailed Design | 2023-08-02 | 2023-08-09 | 3857
A3870 | Prepare and Submitt Electerical Design {Detailed Design} | Submit for approval Detailed Design | 2023-08-02 | 2023-08-09 | 3857
A3880 | Prepare and Submitt Mechanical design {Detailed Design} | Submit for approval Detailed Design | 2023-08-02 | 2023-08-09 | 3857
A3890 | Prepare and Submitt Metal fence Design {Detailed Design} | Submit for approval Detailed Design | 2023-08-02 | 2023-08-09 | 3857
A2270 | 15 watts PA Horn Speaker Outdoor type | ELV works | 2023-08-02 | 2023-08-17 | 4000
A3910 | Approved Cabins Design {Detailed Design} | Approved Detailed Design | 2023-08-08 | 2023-08-15 | 3857
A3760 | Approved Master plan {Schematic Design} | Approved Schematic Designs | 2023-08-10 | 2023-08-17 | 3857
A3920 | Approved Land scape Design {Detailed Design} | Approved Detailed Design | 2023-08-10 | 2023-08-17 | 3857
A3930 | Approved Departure Hall Design {Detailed Design} | Approved Detailed Design | 2023-08-10 | 2023-08-17 | 3857
A3940 | Approved Electerical Design {Detailed Design} | Approved Detailed Design | 2023-08-10 | 2023-08-17 | 3857
A3950 | Approved Mechanical Design {Detailed Design} | Approved Detailed Design | 2023-08-10 | 2023-08-17 | 3857
A3960 | Approved Metal fence Design {Detailed Design} | Approved Detailed Design | 2023-08-10 | 2023-08-17 | 3861
A3680 | Cabins Submittal | Procurement | 2023-08-16 | 2023-08-17 | 0
A1590 | Mosque with Toilets Reinforced Concrete | Civil works | 2023-08-17 | 2023-09-16 | 420000
A3720 | Structural Works Customs and Immigraton | Civil works | 2023-08-17 | 2023-12-26 | 600000
A3830 | Prepare and Submitt Master plan {Detailed Design} | Submit for approval Detailed Design | 2023-08-17 | 2023-08-24 | 3857
A3990 | Electerical Material Submittal | Procurement | 2023-08-17 | 2023-08-20 | 0
A4020 | Metal fence Material Submittal | Procurement | 2023-08-17 | 2023-08-20 | 0
A4050 | Mechanical Material Submittal | Procurement | 2023-08-17 | 2023-08-20 | 0
A3600-30 | Schematic Design Finish Date | Milestones |  | 2023-08-17 | 0
A3600-40 | Final Design Start Date | Milestones | 2023-08-17 |  | 0
A3600-60 | Procurment Start Date | Milestones | 2023-08-17 |  | 0
A3600-80 | Procurment FINISH Date | Milestones | 2023-08-17 |  | 0
A2280 | Audio Amplifier 100W with IP connectivity | ELV works | 2023-08-17 | 2023-09-02 | 20000
A4000 | Electerical Material Approval | Procurement | 2023-08-20 | 2023-08-22 | 0
A4030 | Metal fence Material Approval | Procurement | 2023-08-20 | 2023-08-22 | 0
A4060 | Mechanical Material Approval | Procurement | 2023-08-20 | 2023-08-22 | 0
A3160 | Construct New Concrete Islands | Civil works | 2023-08-21 | 2023-09-10 | 154000
A4010 | Electerical Material Po | Procurement | 2023-08-22 | 2023-08-24 | 0
A4040 | Metal fence Material Po | Procurement | 2023-08-22 | 2023-08-24 | 0
A4070 | Mechanical Material Po | Procurement | 2023-08-22 | 2023-08-24 | 0
A3690 | Cabins Approval | Procurement | 2023-08-24 | 2023-08-26 | 0
A1200 | Supply and install of SMDB Pillar | Electrical works | 2023-08-24 | 2023-09-17 | 20000
A1330 | Cabinets/Telecom Rooms | Civil works | 2023-08-24 | 2023-09-23 | 90000
A1480 | install cables from MDB to SMDB | Electrical works | 2023-08-24 | 2023-09-07 | 220
A1760 | street lighting poles for parking | Electrical works | 2023-08-24 | 2023-09-11 | 117000
A1800 | install cables from LCP to lighting poles | Electrical works | 2023-08-24 | 2023-09-13 | 176000
A2010 | Water supply network pipe | Mechanical works | 2023-08-24 | 2023-09-23 | 20000
A2110 | Firefighting pipes | Mechanical works | 2023-08-24 | 2023-09-07 | 8100
A2470 | install street lighting poles parking area | Electrical works | 2023-08-24 | 2023-09-23 | 270000
A2660 | Water supply pipe | Mechanical works | 2023-08-24 | 2023-09-09 | 20000
A2770 | First Fix for Security [SFT] | ELV works | 2023-08-24 | 2023-09-09 | 19500
A3120 | install cables from LCP to lighting poles | Electrical works | 2023-08-24 | 2023-09-11 | 120000
A3900 | Approved Master plan {Detailed Design} | Approved Detailed Design | 2023-08-24 | 2023-09-02 | 3857
A3700 | Cabins Po | Procurement | 2023-08-27 | 2023-08-28 | 0
A1020 | Provide New Prefabricated Security | Civil works | 2023-08-29 | 2023-09-26 | 150000
A1320 | Provide New Prefabricated cabins | Civil works | 2023-08-29 | 2023-09-26 | 150000
A2330 | Provide New Prefabricated Security | Civil works | 2023-08-29 | 2023-09-19 | 240000
A2340 | Cabinets/Telecom Rooms | Civil works | 2023-08-29 | 2023-09-16 | 120000
A2960 | Cabinets/Telecom Rooms | Civil works | 2023-08-29 | 2023-09-14 | 60000
A2290 | IP Base PA system Equipment rack | ELV works | 2023-09-02 | 2023-09-17 | 20000
A3600-50 | Final Design Finish Date | Milestones |  | 2023-09-02 | 0
A1410 | Execute Road Works | Civil works | 2023-09-03 | 2023-09-24 | 36000
A3460 | Soil Preperation | landscaping | 2023-09-03 | 2023-09-19 | 78000
A3710 | Sidewalks Material Submittal | Procurement | 2023-09-03 | 2023-09-04 | 0
A3600-70 | Construction Start Date | Milestones | 2023-09-03 |  | 0
A1060 | Direct Buried ELV Duct | ELV work side wide | 2023-09-05 | 2023-09-30 | 360000
A3970 | Sidewalks Material Approval | Procurement | 2023-09-05 | 2023-09-06 | 0
A3980 | Sidewalks Material Po | Procurement | 2023-09-07 | 2023-09-09 | 0
A2090 | Manual fire extinguisher DRY Chemical Powder | Mechanical works | 2023-09-07 | 2023-09-23 | 3200
A2680 | Sewage pipe | Mechanical works | 2023-09-09 | 2023-09-24 | 25000
A1430 | Curb Stone | Civil works | 2023-09-10 | 2023-10-08 | 64000
A1740 | Curb Stone | Civil works | 2023-09-10 | 2023-10-08 | 160000
A2780 | 3x50mm dia PVC duct bank | ELV works | 2023-09-10 | 2023-09-25 | 20000
A3230 | Construction of Fence | Civil works | 2023-09-10 | 2023-10-04 | 355500
A1770 | street lighting for Bus Outbound | Electrical works | 2023-09-11 | 2023-09-25 | 72000
A3110 | install exterior cables from MDB to LCP | Electrical works | 2023-09-11 | 2023-09-27 | 44000
A1830 | install cables from Lighting panel boards | Electrical works | 2023-09-13 | 2023-10-03 | 209000
A3060 | Construct Median withInterlocking Tiles | Civil works | 2023-09-14 | 2023-10-01 | 65000
A1030 | Cabinets/Telecom Rooms | Civil works | 2023-09-14 | 2023-09-30 | 30000
A1600 | Mosque with Toilets | Civil works | 2023-09-16 | 2023-10-15 | 600000
A2440 | Construct Median with Interlocking | Civil works | 2023-09-16 | 2023-10-08 | 250000
A2550 | GFCI power sockets for Immigraton Building | Electrical works | 2023-09-16 | 2023-09-21 | 7500
A1210 | Supply and install electrical cables | Electrical works | 2023-09-17 | 2023-10-02 | 25000
A2300 | Single Data outlet RJ46 for CCTV cameras | ELV works | 2023-09-17 | 2023-10-01 | 1400
A1500 | install Automatic Transfer Switch | Electrical works | 2023-09-18 | 2023-10-03 | 20000
A3470 | Ziziphus spina-Christi , Tree | landscaping | 2023-09-19 | 2023-10-03 | 90000
A2410 | Supply and Install Tire Shredder | Civil works | 2023-09-19 | 2023-10-18 | 20000
A2710 | AC Direct expansion split unit 18000 | Mechanical works | 2023-09-19 | 2023-10-11 | 12000
A2620 | install Automatic Transfer Switch | Electrical works | 2023-09-21 | 2023-10-07 | 35000
A1420 | Construct Median | Civil works | 2023-09-23 | 2023-10-22 | 67500
A2020 | An electric water heater | Mechanical works | 2023-09-23 | 2023-10-02 | 3200
A2650 | install uninterruptible power supply | Electrical works | 2023-09-23 | 2023-10-14 | 48000
A2040 | Rain water pipes | Mechanical works | 2023-09-23 | 2023-10-08 | 8000
A1380 | First and Second Fix Barriers | Civil works | 2023-09-24 | 2023-10-23 | 100000
A1780 | install of lighting control pillar for Bus Outbound | Electrical works | 2023-09-25 | 2023-10-02 | 15000
A2790 | Smoke Detectors | ELV works | 2023-09-25 | 2023-10-10 | 7800
A1050 | Supply and install curbs for cabins | Civil works | 2023-09-27 | 2023-10-11 | 9600
A1350 | Supply and install curbs | Civil works | 2023-09-27 | 2023-10-18 | 12000
A3100 | install of lighting control pillar | Electrical works | 2023-09-27 | 2023-10-12 | 15000
A1040 | Construct New Concrete Islands | Civil works | 2023-09-30 | 2023-10-15 | 12500
A1070 | Concrete Encased ELV Duct | ELV work side wide | 2023-09-30 | 2023-10-11 | 140000
A2970 | Construct New Concrete Islands | Civil works | 2023-10-01 | 2023-10-15 | 7500
A2310 | Single Data outlet RJ46 for IP Telephone | ELV works | 2023-10-01 | 2023-10-16 | 1400
A1220 | Supply and install electrical cables | Electrical works | 2023-10-02 | 2023-10-17 | 18000
A1930 | install power panel board for Immigration Hall | Electrical works | 2023-10-03 | 2023-10-31 | 12000
A1530 | install cables from LCP to lighting poles | Electrical works | 2023-10-03 | 2023-11-01 | 209000
A1790 | install cables from MDB to LCP | Electrical works | 2023-10-03 | 2023-10-24 | 200000
A3480 | Carissa green carpet | landscaping | 2023-10-03 | 2023-10-25 | 180000
A3210 | Construction of Speed Humps | Civil works | 2023-10-04 | 2023-10-19 | 12000
A2590 | install cables from MDB to distribution board | Electrical works | 2023-10-07 | 2023-10-23 | 45000
A2030 | Sewage pipe for Customs building | Mechanical works | 2023-10-08 | 2023-10-23 | 25000
A2350 | Construct New Concrete Islands | Civil works | 2023-10-08 | 2023-10-23 | 9000
A1360 | Execute Cabin Protection Works | Civil works | 2023-10-09 | 2023-11-06 | 40000
A2800 | Manual pull station | ELV works | 2023-10-10 | 2023-10-15 | 8000
A2700 | AC Direct expansion split unit 36000 | Mechanical works | 2023-10-11 | 2023-11-02 | 76500
A1160 | Supply and Install Tire Shredder | Civil works | 2023-10-11 | 2023-10-26 | 20000
A3090 | install street lighting poles | Electrical works | 2023-10-12 | 2023-11-01 | 180000
A2610 | Installation of Generator | Electrical works | 2023-10-15 | 2023-11-02 | 150000
A2810 | Horn with Strobes | ELV works | 2023-10-15 | 2023-10-29 | 7200
A1610 | Provide New Prefabricated | Civil works | 2023-10-15 | 2023-11-01 | 120000
A2120 | Water supply pipes for Masjid | Mechanical works | 2023-10-15 | 2023-10-30 | 20000
A2190 | PVC duct bank for Masjid | ELV works | 2023-10-15 | 2023-11-13 | 15000
A1150 | Construction of Speed Humps | Civil works | 2023-10-15 | 2023-10-30 | 12000
A3020 | Construction of Speed humps | Civil works | 2023-10-15 | 2023-10-30 | 12000
A2320 | 12U Equipment and communication cabinet | ELV works | 2023-10-16 | 2023-10-31 | 15000
A1230 | Generator Supply and Installation | Electrical works | 2023-10-17 | 2023-11-02 | 80000
A1400 | Supply and Install Tire Shredder | Civil works | 2023-10-18 | 2023-11-09 | 20000
A3260 | Curb Stone | Civil works | 2023-10-19 | 2023-11-06 | 108000
A1340 | Construct New Concrete Islands | Civil works | 2023-10-22 | 2023-11-12 | 7500
A2360 | install curbs for cabins | Civil works | 2023-10-23 | 2023-11-06 | 16000
A2420 | Construction of Fence | Civil works | 2023-10-23 | 2023-11-12 | 180000
A2050 | AC Direct expansion split unit 36000 | Mechanical works | 2023-10-23 | 2023-11-21 | 76500
A2560 | install Distribution board | Electrical works | 2023-10-23 | 2023-11-07 | 20000
A1820 | install cables from MDB to SMDB | Electrical works | 2023-10-24 | 2023-11-12 | 150000
A3490 | Pennisetum Setaceum shrub | landscaping | 2023-10-25 | 2023-11-11 | 60000
A1130 | Supply and Install Traffic Lights | Civil works | 2023-10-26 | 2023-11-11 | 15000
A2820 | Fire Alarm Control Panel with IP connectivity | ELV works | 2023-10-29 | 2023-11-13 | 25000
A1120 | Execute Cabin Protection Works | Civil works | 2023-10-30 | 2023-11-20 | 40000
A2210 | Manual pull station for Masjid | ELV works | 2023-10-30 | 2023-11-21 | 4000
A3070 | Curb Stone | Civil works | 2023-10-30 | 2023-11-15 | 56000
A2230 | ELV System- Fire Alarm Detection | ELV works | 2023-10-31 | 2023-11-22 | 25000
A1940 | install sub-main distribution board for Masjed | Electrical works | 2023-11-01 | 2023-11-29 | 30000
A3130 | install uninterruptible power supply | Electrical works | 2023-11-01 | 2023-11-18 | 80000
A1520 | install cables from MDB to LCP | Electrical works | 2023-11-01 | 2023-11-18 | 66000
A1620 | Cabinets/Telecom Rooms | Civil works | 2023-11-01 | 2023-11-18 | 30000
A2670 | An electric water heater | Mechanical works | 2023-11-02 | 2023-11-16 | 3200
A2580 | lighting panel board for Immigraton Building | Electrical works | 2023-11-02 | 2023-11-18 | 20000
A3300 | Demolition Works - Buildings | Civil works | 2023-11-06 | 2023-11-23 | 137500
A2380 | Supply and Install Traffic Lights | Civil works | 2023-11-06 | 2023-11-28 | 24000
A2630 | install EDB pillar | Electrical works | 2023-11-07 | 2023-11-22 | 20000
A1370 | Supply and Install Traffic Lights | Civil works | 2023-11-09 | 2023-12-02 | 15000
A1170 | Supply and Install Traffic Sign | Civil works | 2023-11-11 | 2023-11-26 | 12000
A3500 | Beige Gravels | landscaping | 2023-11-11 | 2023-11-26 | 25000
A2400 | Construction of Speed humps | Civil works | 2023-11-12 | 2023-11-26 | 12000
A1840 | install cables from Power panel boards | Electrical works | 2023-11-12 | 2023-12-03 | 209000
A1390 | Construction of Speed Humps | Civil works | 2023-11-13 | 2023-11-13 | 12000
A1440 | Execute Road Marking | Civil works | 2023-11-13 | 2023-12-04 | 24000
A2200 | Smoke Detectors for Masjid | ELV works | 2023-11-13 | 2023-12-12 | 4320
A2830 | Dual Head Emergency lights with battery | ELV works | 2023-11-13 | 2023-11-20 | 8000
A3050 | Execute Asphalt Re-spreading | Civil works | 2023-11-15 | 2023-12-02 | 45000
A3360 | install cables from LCP to lighting poles | Electrical works | 2023-11-15 | 2023-12-14 | 120000
A2720 | Ceiling mounted Kitchen Exhaust fan | Mechanical works | 2023-11-16 | 2023-11-23 | 3000
A2600 | Lightning Protection and Grounding System | Electrical works | 2023-11-18 | 2023-12-03 | 35000
A1240 | Supply and install Automatic Transfer Switch | Electrical works | 2023-11-18 | 2023-12-03 | 20000
A1630 | Construct New Concrete Islands | Civil works | 2023-11-18 | 2023-12-03 | 7500
A1540 | install cables from SMDB to 9 new cabins | Electrical works | 2023-11-18 | 2023-12-09 | 198000
A1810 | install uninteruptible power supply | Electrical works | 2023-11-20 | 2023-12-19 | 32000
A2840 | Power Socket Outlet for emergency light | ELV works | 2023-11-20 | 2023-12-05 | 3500
A1140 | First and Second Fix for Gate Barriers | Civil works | 2023-11-20 | 2023-12-12 | 120000
A2060 | AC Direct expansion split unit 18000 | Mechanical works | 2023-11-21 | 2023-11-28 | 12000
A2220 | Horn with Strobes | ELV works | 2023-11-22 | 2023-12-06 | 4500
A2490 | install Electrical cables from DB to LCP | Electrical works | 2023-11-22 | 2023-12-07 | 37500
A3320 | Demolition Works - Curbs | Civil works | 2023-11-23 | 2023-12-10 | 31500
A2730 | Ceiling mounted toilet Exhaust fan | Mechanical works | 2023-11-23 | 2023-12-02 | 6000
A2450 | Curb Stone | Civil works | 2023-11-26 | 2023-12-25 | 200000
A3510 | Waste bin receptacles | landscaping | 2023-11-26 | 2023-12-12 | 30000
A2070 | Ceiling mounted Kitchen Exhaust fan | Mechanical works | 2023-11-28 | 2023-12-05 | 3000
A2750 | Fire hose cabinets | Mechanical works | 2023-12-02 | 2023-12-16 | 14000
A2990 | Execute Cabin Protection Works | Civil works | 2023-12-02 | 2023-12-18 | 64000
A1640 | Install curbs for cabins | Civil works | 2023-12-03 | 2023-12-17 | 7200
A1250 | Supply and install EDB power supply | Electrical works | 2023-12-03 | 2023-12-18 | 15000
A2000 | Install Cables from SMDB to Coffee DB | Electrical works | 2023-12-03 | 2023-12-18 | 22000
A2570 | Power Panel board for Immigraton Building | Electrical works | 2023-12-03 | 2023-12-18 | 20000
A2850 | 10 watts PA Horn Speaker Indoor type | ELV works | 2023-12-05 | 2023-12-19 | 10800
A2080 | Ceiling mounted toilet Exhaust fan | Mechanical works | 2023-12-05 | 2023-12-13 | 6000
A2500 | install Electrical cables from LCP to lighting poles | Electrical works | 2023-12-07 | 2023-12-28 | 210000
A1510 | install EDB power supply pillar | Electrical works | 2023-12-09 | 2023-12-24 | 15000
A3310 | Demolition Works - Medians | Civil works | 2023-12-10 | 2023-12-26 | 60000
A3520 | Benches | landscaping | 2023-12-12 | 2023-12-27 | 28000
A2240 | Dual Head Emergency lights | ELV works | 2023-12-12 | 2023-12-26 | 4000
A1190 | Overhead Cantilever Traffic Sign | Civil works | 2023-12-12 | 2024-01-04 | 120000
A2100 | Fire hose cabinets | Mechanical works | 2023-12-13 | 2023-12-27 | 14000
A3350 | install cables from MDB to LCP | Electrical works | 2023-12-14 | 2024-01-06 | 44000
A2760 | Firefighting pipes network | Mechanical works | 2023-12-16 | 2023-12-24 | 8100
A1650 | Execute Cabin Protection Works | Civil works | 2023-12-17 | 2024-01-02 | 32000
A1260 | electrical Cables from EDB to DB's | Electrical works | 2023-12-18 | 2024-01-08 | 200000
A3080 | Execute Road Marking | Civil works | 2023-12-18 | 2024-01-02 | 36000
A1980 | Install Cables from SMDB to Immigration Hall DB | Electrical works | 2023-12-18 | 2024-01-02 | 39600
A2160 | AC Direct expansion split unit | Mechanical works | 2023-12-18 | 2024-01-09 | 52500
A2860 | 15 watts PA Horn Speaker Outdoor type | ELV works | 2023-12-19 | 2024-01-03 | 8000
A2740 | Manual fire extinguisher DRY powder | Mechanical works | 2023-12-24 | 2023-12-31 | 3600
A1560 | install uninterruptible power supply | Electrical works | 2023-12-24 | 2024-01-09 | 40000
A2370 | Execute Cabin Protection Works | Civil works | 2023-12-25 | 2024-01-10 | 64000
A3240 | Execute Asphalt Re-surfacing | Civil works | 2023-12-26 | 2024-01-11 | 45000
A-11000 | Masonry Works | Civil works | 2023-12-26 | 2024-01-24 | 300000
A2250 | Power Socket Outlet for emergency light | ELV works | 2023-12-26 | 2024-01-10 | 1750
A3530 | manual fire extinguisher (Dry powder) | landscaping | 2023-12-27 | 2024-01-03 | 1800
A2640 | Install electrical LV Cables from EDB to DB | Electrical works | 2023-12-28 | 2024-01-24 | 400000
A2690 | Rain water Drainage pipes | Mechanical works | 2023-12-31 | 2024-01-07 | 8000
A1660 | Install Traffic Lights | Civil works | 2024-01-02 | 2024-01-16 | 12000
A3040 | Execute Road Works | Civil works | 2024-01-02 | 2024-01-18 | 36000
A1990 | Install Cables from SMDB to Masjed DB | Electrical works | 2024-01-02 | 2024-01-18 | 39600
A3540 | manual fire extinguisher FOAM type | landscaping | 2024-01-03 | 2024-01-10 | 3000
A2870 | Audio Amplifier 100W with IP connectivity | ELV works | 2024-01-03 | 2024-01-20 | 40000
A1180 | Overhead Traffic Sign Gantries | Civil works | 2024-01-04 | 2024-02-03 | 200000
A3340 | install of lighting control pillar | Electrical works | 2024-01-06 | 2024-01-21 | 15000
A1270 | install cables from SMDB to LCP | Electrical works | 2024-01-08 | 2024-01-24 | 50000
A2130 | An electric water heater | Mechanical works | 2024-01-09 | 2024-01-23 | 3200
A1490 | Installation of Generator | Electrical works | 2024-01-09 | 2024-01-25 | 80000
A3550 | A manual fire extinguisher dry carried on wheeld type | landscaping | 2024-01-10 | 2024-01-25 | 16000
A2460 | Execute Road Marking | Civil works | 2024-01-10 | 2024-02-01 | 90000
A3180 | Execute Cabin Protection Works | Civil works | 2024-01-11 | 2024-01-27 | 24000
A1670 | First and Second Fix for Gate | Civil works | 2024-01-16 | 2024-02-03 | 80000
A3010 | First and Second Fix for Gate | Civil works | 2024-01-18 | 2024-02-06 | 160000
A1880 | install exit lights for buildings and cabins | Electrical works | 2024-01-18 | 2024-01-25 | 8000
A2880 | IP Base PA system Equipment rack | ELV works | 2024-01-20 | 2024-02-04 | 20000
A3330 | install street lighting poles for New Parking | Electrical works | 2024-01-21 | 2024-02-19 | 180000
A2180 | Manual fire extinguisher DRY powder | Mechanical works | 2024-01-23 | 2024-02-07 | 1600
A2530 | install exit lights for Immigraton Building | Electrical works | 2024-01-24 | 2024-02-07 | 9000
A1280 | Supply and install lighting poles | Electrical works | 2024-01-24 | 2024-02-11 | 90000
A-11010 | Finishes | Civil works | 2024-01-24 | 2024-02-22 | 300000
A3570 | A manual fire extinguisher Foam carried on wheeld | landscaping | 2024-01-25 | 2024-02-12 | 26000
A1900 | install GFCI power sockets for buildings and cabins | Electrical works | 2024-01-25 | 2024-02-01 | 7500
A1550 | Lightning Protection and Grounding System | Electrical works | 2024-01-25 | 2024-02-11 | 25000
A3270 | Execute Road Marking | Civil works | 2024-01-27 | 2024-02-11 | 36000
A1860 | install Interior lighting fixtures for buildings | Electrical works | 2024-02-01 | 2024-02-10 | 51750
A1680 | Construction of Speed Humps | Civil works | 2024-02-03 | 2024-02-18 | 12000
A2890 | Duplex Data outlet RJ45 for work stations | ELV works | 2024-02-04 | 2024-02-18 | 14000
A2950 | Provide New Prefabricated | Civil works | 2024-02-06 | 2024-02-28 | 240000
A2150 | Rain water drainage pipes | Mechanical works | 2024-02-07 | 2024-02-22 | 8000
A2510 | install Interior lighting fixtures for Immigraton | Electrical works | 2024-02-07 | 2024-02-25 | 75000
A2430 | Execute Road Works | Civil works | 2024-02-08 | 2024-03-09 | 1440000
A1870 | lighting fixtures with battery pack for buildings | Electrical works | 2024-02-10 | 2024-03-02 | 14000
A1920 | install lighting panel board for Immigration Hall | Electrical works | 2024-02-10 | 2024-02-17 | 12000
A1460 | Supply and install of lighting | Electrical works | 2024-02-11 | 2024-02-25 | 15000
A1290 | Lightning Protection and Grounding | Electrical works | 2024-02-11 | 2024-02-26 | 25000
A3200 | First and Second Fix for Gate | Civil works | 2024-02-11 | 2024-02-27 | 60000
A3580 | Automatic fire extinguisher Co2 type for electrical rooms | landscaping | 2024-02-12 | 2024-02-19 | 2200
A1950 | install lighting panel board for Masjed | Electrical works | 2024-02-17 | 2024-02-24 | 12000
A1690 | Supply and Install Tire Shredder | Civil works | 2024-02-18 | 2024-03-04 | 20000
A2900 | Single Data outlet RJ46 for WIFI | ELV works | 2024-02-18 | 2024-03-04 | 4200
A3370 | install UPS | Electrical works | 2024-02-19 | 2024-03-05 | 24000
A2140 | Sewage pipes | Mechanical works | 2024-02-22 | 2024-03-09 | 25000
A-11020 | Soft Finishes | Civil works | 2024-02-22 | 2024-03-23 | 265521.5
A1960 | install power panel board for Masjed | Electrical works | 2024-02-24 | 2024-03-02 | 12000
A2520 | install Interior lighting with battery | Electrical works | 2024-02-25 | 2024-03-11 | 21250
A1450 | Supply and install of SMDB | Electrical works | 2024-02-25 | 2024-03-13 | 30000
A1300 | install cables from LCP to lighting poles | Electrical works | 2024-02-26 | 2024-03-26 | 150000
A3140 | Provide New Prefabricated | Civil works | 2024-02-27 | 2024-03-16 | 90000
A2980 | Supply and install curbs | Civil works | 2024-02-28 | 2024-03-13 | 12000
A1890 | install power sockets for buildings and cabins | Electrical works | 2024-03-02 | 2024-03-10 | 19250
A1700 | Construction of Fence | Civil works | 2024-03-04 | 2024-03-24 | 202500
A2910 | Single Data outlet RJ46 for IP Telephone | ELV works | 2024-03-04 | 2024-03-11 | 7000
A2170 | Wall mounted Exhaust Fan | Mechanical works | 2024-03-09 | 2024-03-10 | 9600
A2390 | First and Second Fix for Gate | Civil works | 2024-03-09 | 2024-04-07 | 260000
A1850 | install street lighting poles | Electrical works | 2024-03-10 | 2024-03-19 | 135000
A2540 | power sockets for Immigraton Building | Electrical works | 2024-03-11 | 2024-03-26 | 35000
A2920 | Data outlet RJ46 for CCTV cameras/ Security system | ELV works | 2024-03-11 | 2024-03-19 | 10500
A1470 | Supply and install street lighting | Electrical works | 2024-03-13 | 2024-04-02 | 180000
A3030 | Supply and Install Tire Shredder | Civil works | 2024-03-13 | 2024-03-28 | 20000
A3290 | Remove and re-install fence | Civil works | 2024-03-16 | 2024-04-04 | 200000
A3420 | Wet utilities House Connections (sewage) | Wet utilties works | 2024-03-16 | 2024-03-31 | 18000
A2930 | 42U Equipment and communication cabinet | ELV works | 2024-03-19 | 2024-03-26 | 50000
A1910 | install sub-main distribution board | Electrical works | 2024-03-19 | 2024-03-27 | 30000
A1710 | Supply and install metal gates | Civil works | 2024-03-24 | 2024-04-09 | 36000
A2940 | 12U Equipment and communication cabinet | ELV works | 2024-03-26 | 2024-04-02 | 30000
A1310 | Supply and install uninterruptible power supply | Electrical works | 2024-03-26 | 2024-04-02 | 40000
A2480 | Supply and install of lighting control pillar | Electrical works | 2024-03-26 | 2024-04-03 | 15000
A1970 | install sub-main distribution board for Coffee | Electrical works | 2024-03-27 | 2024-04-03 | 12000
A3000 | Supply and Install Traffic Lights | Civil works | 2024-03-28 | 2024-04-07 | 24000
A3380 | Wet utilities House connections (water) | Wet utilties works | 2024-03-31 | 2024-04-15 | 18000
A3170 | Supply and install curbs | Civil works | 2024-04-04 | 2024-04-20 | 5200
A1720 | Execute Road Works | Civil works | 2024-04-09 | 2024-04-27 | 104000
A3430 | Wet utilities Irrigation water Connections | Wet utilties works | 2024-04-15 | 2024-05-14 | 100000
A3280 | Supply and install Shaded Walkway | Civil works | 2024-04-20 | 2024-05-12 | 266000
A1730 | Construct Median | Civil works | 2024-04-27 | 2024-05-16 | 200000
A3220 | Supply and Install Tire Shredder | Civil works | 2024-05-12 | 2024-05-27 | 20000
A3390 | Wet utilities Overhead Water Tank | Wet utilties works | 2024-05-14 | 2024-05-29 | 12000
A1750 | Execute Road Marking | Civil works | 2024-05-16 | 2024-05-25 | 60000
A3190 | Supply and Install Traffic Lights | Civil works | 2024-05-27 | 2024-06-11 | 9000
A3440 | Misting fans for shaded walk way area | Mechanical works | 2024-05-27 | 2024-06-11 | 21000
A3410 | Wet utilities Water Pumps | Wet utilties works | 2024-05-29 | 2024-06-27 | 75000
A3450 | Misting pumps and its network | Mechanical works | 2024-06-11 | 2024-06-26 | 30000
A3400 | Wet utilities Water tank (burried) | Wet utilties works | 2024-06-27 | 2024-07-04 | 18000
A3660 | Testing & Commissioning | Testing & Commissioning | 2024-07-04 | 2024-07-11 | 0
A3600-10 | Construction Finish Date | Milestones |  | 2024-07-04 | 0
A3670 | Handover | Handover | 2024-07-11 | 2024-07-16 | 0
A3600 | PROJECT FINISH Date | Milestones | 2024-07-16 | 2024-07-16 | 0